## Action Plan
PROJECT NAME | [7 empty] | PROGRESS LOG
Iteration 1 | [7 empty] | Iteration 1
ACTIVITY | RESPONSIBLE | Due Date | STATUS | START | END | NOTES | Date | ACTIVITY | NOTES
#1: Vision Document | Tomal H. | Jan 27th | Complete | Jan 26th | Jan 27th |  | Jan 26th | Assigned task to everyone
#2: Data Dictionary | Tomal H. | Jan 27th | In Progress | Jan 26th |  |  | Jan 28th | Checked the progress and Revised Vision Document and UI Sketch
#3: Actors and Their Goals | Sanuda | Jan 27th | In Progress | Jan 26th | Jan 28th
#4: USD - Set up a game | Salman | Jan 27th | Complete | Jan 26th | Jan 27th
#5: USD - Take a turn | Dilhan | Jan 28th | In Progress | Jan 26th
#6: UI Sketch - Set up a Game | Salman | Jan 27th | Complete | Jan 26th | Jan 27th
#7: UI Sketch - Take a turn | Salman |  | Not Started | Jan 27th
#8: Brief Use Case Description | Mohammad | Jan 27th | In Progress | Jan 26th
#9: Domain Model | Tomal & Sanuda |  | Not Started | Jan 28th
#10: Plan for Iteration 2 | NA

## Action Plan - BLANK
ACTION PLAN
PROJECT NAME | PROJECT MANAGER
ACTION | RESPONSIBLE | PRIORITY | STATUS | START | END | NOTES
Goal #1:
Goal #2:
Goal #3:
Goal #4: