## Action Plan - BLANK
PROJECT NAME | [7 empty] | PROGRESS LOG
Iteration 3 | [7 empty] | Iteration 3
ACTIVITY | RESPONSIBLE | Due Date | STATUS | START | END | NOTES | Date | ACTIVITY | NOTES
#1: Revise Use Case Description | Mohammad/Dilhan |  | Not Started |  | - |  | March 4th | Assigned task to everyone
#2: Revise Sequence Diagram | Sanuda/Tomal |  | Not Started |  | -
#3: UCD - Moving a Barricade | Tomal | 14th March | Not Started
#4: UCD - First move of the token | Salman | 15th March | Finished |  | 14th March
#5: Sequence Diagram 1 | Mohammad | 17th March | Not Started
#6: Sequence Diagram 2 | Dilhan | 17th March | Finished |  | 7th March
#7: Logical Architecture Diagram | Salman | 15th March | Not Started
#8: 2nd Minor release | Everyone | 17th March | Not Started
Set up the grid | Sanuda | 13th March | Finished |  | 14th March
Moving up pieces | Dilhan | 15th March
Setting up barricade | Mohammad/Tomal | 16th March