## Action Plan
PROJECT NAME
Iteration 1
ACTION | RESPONSIBLE | PRIORITY | STATUS | START | END | NOTES
#1: Vision Document | Tomal H. |  | Complete | Jan 26th | Jan 27th
#2: Data Dictionary | Tomal H. |  | In Progress | Jan 26th
#3: Actors and Their Goals | Sanuda |  | In Progress | Jan 26th
#4: USD - Set up a game | Salman |  | Complete | Jan 26th | Jan 27th
#5: USD - Take a turn | Dilhan |  | In Progress | Jan 26th
#6: UI Sketch - Set up a Game | Salman |  | Complete | Jan 26th | Jan 27th
#7: UI Sketch - Take a turn | Salman |  | Not Started | Jan 27th
#8: Brief Use Case Description | Mohammad |  | In Progress | Jan 26th
#9: Domain Model | Not Assigned
#10: Plan for Iteration 2 | NA

## Action Plan - BLANK
ACTION PLAN
PROJECT NAME | PROJECT MANAGER
ACTION | RESPONSIBLE | PRIORITY | STATUS | START | END | NOTES
Goal #1:
Goal #2:
Goal #3:
Goal #4: